## Effort Estimation Github Issues
Summary of tasks | Estiamte (hours) | Coding Effort (hours) | Non-Coding Effort (hours) | Estimator | Implementors
Department of Labor and Industrial Relations (DLIR) Hawaii Unemployment Insurance Modernization (HUI Huaka'i) Project | 1 | 0 | 1.5 | CourtneyHisa | CourtneyHisa
Department of Human Services (DHS) HANA Modernization Project | 1 | 0.5 | 0.5 | kylersm | kylersm
Department Attorney General (ATG) CSEA Keiki Replatform Off Mainframe Project | 1 | 3 | 0.5 | shuto | shuton-gif
Department of Human Services (DHS) Child Welfare Services Branch HI-THRIVE Modernization Project | 1.5 | 0 | 1.5 | zhanpeng | zhanpeng
Department of Human Services (DHS) Systems Modernization Project | 2 | 0 | 1 | shuton-gif | shuton-gif
DCCA Public Utilities Commission (PUC) Content and Document Management System (CDMS) Project | 2 | 0 | 2.5 | zhanpeng | zhanpenglin9
DOH Behavioral Health Administration (BHA) Alcohol and Drug Abuse Division (ADAD) INSPIRE-PLUS Case Management Solution Project | 2 | 0 | 1.5 | zhanpeng | zhanpenglin9
Department of Commerce and Consumer Affairs (DCCA) Business Registration Modernization (BRM) Project | 1 | 0.1 | 1 | kylersm | kylersm
DOH Behavioral Health Administration (BHA) Integrated Case Management System Project | 1 | 0 | 1.5 | kylersm | kylersm
DOT-Highways Financial Management Systems Project | 1 | 0 | 1 | zhanpeng | zhanpeng
Dark theme | 3 | 4 | 0 | kylersm | kylersm
Update Homepage | 0.25 | 0.25 | 0 | zhanpeng | zhanpeng
Security Watch | 1 | 2 | 0 | kylersm | kylersm
additionally, polish the sign-in/log-out screens | 4 | 2.5 | 2 | zhanpeng | zhanpeng
Standardize form layouts – e.g. decide how buttons should look for each form | 2 | 2.5 | 1 | zhanpeng | zhanpeng
Delete comment page and provide comment options on project page | 2 | 2 | 0.5 | zhanpeng | zhanpeng
About Page | 0.08 | 0.16 | 0 | zhanpeng | zhanpeng
login page | 2.5 | 5 | 2 | zhanpeng | zhanpeng
Add a card view for dashboard page | 2 | 1 | 2 | shuton-gif | shuton-gif
fix time line table | 4 | 3 | 1 | shuton-gif | shuton-gif
Fix /project/[id] looks | 1 | 1 | 1 | shuton-gif | shuton-gif
Add approvable system for reports | 1 | 3 | 0.5 | kylersm | kylersm
Search system for dashboards | 2 | 4 | 0 | kylersm | kylersm
Fix current project errors; fix editing comments | 0.2 | 0.2 | 0 | kylersm | kylersm
Make distinction between test-project pages and real project page | 0.5 | 1 | 0 | kylersm | kylersm
UI Housekeeping 2: NextJS links, bootstrap components | 1 | 1 | 0 | kylersm | kylersm
Playwright Tests for All Pages | 2 | 2 | 0 | kylersm | kylersm
Project Milestone 2 Deadline | 2 | 0 | 1.2 | kylersm | kylersm
Connect Dashboard to Database | 1 | 1 | 4 | courtneyhisa | CourtneyHisa
Housekeeping for UI | 2 | 1 | 1.5 | courtneyhisa | CourtneyHisa
Project Payment | 0.5 | 0.5 | 0.25 | courtneyhisa | CourtneyHisa
Add a back button | 0.2 | 0.1 | 0 | kylersm | kylersm

## Team Member Experience and Effo
Team Member | Software Development Experience (months) | How was coding effort tracked | How was non-coding effort tracked?
Kyler Ching | 52 | timed in my head | timed in my head
Courtney Hisamoto | 48 | recorded start time and end time, then calculated time spent | recorded start time and end time, then calculated time spent
Zhanpeng Lin | 42 | Wrote down start time and end time from the clock and calculated time afterward | Wrote down start time and end time from the clock and calculated time afterward
Shuto Nishida | 48 | using a timer, start to end | using a timer, start to end